Elinor Wonders Why

Story Editing Meeting Notes

February 12th, 2019 5:00PM EST/2:00PM PT

Dial in # 1-888-842-2237

Pin # 2665

Attendees:

Daniel Whiteson- Creator

Jorge Cham – Creator

Katherine Sandford – Story Editor

Michael Foulke – Creators Assistant

Kevin MiCallef – Pipeline Studios - Series Director

Marissa Collyer – Pipeline Studios – Senior Producer

Paul Moncrieffe – Pipeline Studios - Script Coordinator

1.) Process

- Keep in mind that Kevin and animators can do physical comedy gags, it’s a crucial part of the show

- Production will send out hard deadlines way in advance for J&D

- The further the script gets in the process the more deadlines need to be hit in order not to effect production

- The D&J Polish pass is very crucial to hit it’s 2 day deadline

2.) Assumptions

- Please keep the cheat sheet close to your heart

- All be more cognitive of line numbers

- Paul and Kathy will review at D1

- Marissa will review at D2

3.) Script Length

- Striving for a nice charming slow paced show

- The higher the page count the faster the pace of the show to cram everything it

- Overall need scripts more consistent

- Don’t want to go below 12 pages. Between 12-13.5

- Simplified stories - line count has been coming in at 100 -110 lines

- Flagging if scripts are going long ASAP

- Cut scripts down - flag it in notes and J&D will make the final cuts during J&D Polish pass

4.) Ditty’s

- We definitely don’t want to change the ditty’s after D2

- If we do change them Marissa needs an adequate time to get them to the composers

- We can make a little notes in the script to not change - let the writers know early

- The composers will just need a heads up a little bit sooner. Polish would be too late.

5.) Miscellaneous

- Jorge has some personal travel in Late March